CDFA PD/GWSS Progress Report

March 2009

I.  Project Title:  Breeding Pierce’s Disease Resistant Winegrapes.

Reporting period:  October 2008 to March 2009

II. Principal Investigators and Cooperators:

Andrew Walker and Alan Tenscher, Dept. of Viticulture and Enology, University of California, Davis, CA 95616-8749;  awalker@ucdavis.edu

III. List of objectives and description of activities

Objective 1. Breed PD resistant winegrapes through backcross techniques using high quality V. vinifera winegrape cultivars and Xylella fastidiosa resistant selections and sources characterized from our previous efforts.

Objective 2. Continue the characterization of X. fastidiosa resistance and winegrape quality traits (color, tannin, ripening dates, flavor, productivity, etc) in novel germplasm sources, in our breeding populations, and in our genetic mapping populations.

IV. Summary of Research Accomplishments

Objective 1.  The breeding cycle for the development of PD resistant grapes has been reduced to 3 years (seed to seed) using marker-assisted selection (MAS) with the b43-17 resistance sources and their progeny.  Our goal at this point is to introgress our PD and PdR1 resistance sources into a large number of V. vinifera winegrape backgrounds. Until we get to the backcross 4 (BC4) (96.8% V. vinifera), there is not much point to growing very large numbers of progeny from any given cross. Using MAS and the 3-year seed-to-seed cycle we will plant BC4 progeny in 2010.

Table 1 presents the crosses made in 2008 with numbers of seeds and seedlings produced along with the number of progeny that were MAS tested in 2009. The goals of the 2008 crosses were: 1) Use the PdR1 allele from the F8909-08 to broaden the vinifera winegrape lines at the 93.75% vinifera level; 2) Combine PdR1 with the powdery mildew resistance gene Run1 at the 90.6% vinifera level; 3) Combine PdR1 with the LG13 powdery mildew resistance gene REN1 at the 87.5% vinifera level; 4) Use F8909-17 based resistance with diverse vinifera winegrapes to produce resistant progeny at the 87.5% vinifera level; 5) Use the F1 progeny of the homozygous PD resistant b40-14 V. arizonica to produce a breeding and mapping population that is 75% vinifera; 6) use elite winegrapes to broaden and expand the V. shuttleworthii breeding lines producing progeny that are 75% and 87.5% vinifera and 7) Produce rootstocks with PdR1 and broad-based nematode resistance.

During this period, five groups of plants were in testing by the greenhouse screen for X. fastidiosa resistance (Table 2).  Group A tests focused first on a revised set of recombinants from our 2006 breeding populations to aid fine-scale PdR1 mapping efforts. We were able to put 13 recombinant genotypes in the PdR1 present group and 18 in the PdR1 absent group while the presence of PdR1 couldn’t be determined for 5 genotypes. Greenhouse results confirmed recombinant predictions based on the markers and indicated that we are narrowing down the genetic area where PdR1 resides. The results also clarified that by switching to the VVCh14-70 marker from ctg6530 we can reduce the number of recombinants in our MAS testing of breeding lines.  Group B tests evaluated the 75% vinifera, PdR1a allele genotypes used as parents in the 2008 crosses (Tables 1 & 2).  Phenotypic evaluation indicates they are all highly resistant to PD. ELISA results are pending.  Group C and E tests were our first greenhouse screens of BC1 (75% vinifera) progeny that contain resistance from a pure form of V. arizonica b40-14 (which previous tests have shown has very strong resistance but has resistance that is unrelated to PdR1).  Group D tests were done to further streamline the greenhouse screening process and decrease greenhouse space requirements.

Objective 2. Although resistance from other backgrounds is complex and quantitative, which results in few resistant progeny from crosses to vinifera cultivars, we continue to advance a number of lines.  In order to better understand the limits of other PD resistance sources the following resistance sources are being studied:

V. arizonica b42-26  – Xf resistance in the 0023 (D8909-15 (V. rupestris x b42-26) x V. vinifera B90-116) population is strong, but is quantitatively inherited. Quantitative trait locus (QTL) analysis has identified a major QTL that accounts for about 20% of the variability (preliminary results). Previous efforts with the 0023 were focused on table grape breeding, and found that the 0023 population (F1, 1/4 b42-26) had about 30% resistant progeny. This population has a large number of weak genotypes, few females with viable seeds, and generally lacks fertility. The progeny of a cross of a resistant 0023 genotype crossed back to vinifera (BC1) were tested and only 7% were resistant.  We tested the 05347 (vinifera F2-35 x b42-26) population to examine the b42-26 resistance source in a less complex background (without the confounding effect of V. rupestris) was completed last year. In 2007, crosses using elite V. vinifera wine type pollen were made to a number of females in this population and 140 genotypes were planted in 2008, which should flower for the first time in Spring 2009.  This Spring we repeated this, producing 827 seeds, to expand this F1 mapping population.

V. shuttleworthii Haines City – Based on the encouraging greenhouse screen results for this resistance source, in 2008 we made the BC1 (75% vinifera) and BC2 (88% vinifera) using a BC1 from our earlier table grape work that was very resistant and had reasonable wine grape characteristics (Table 1e). If we can develop reliable genetic markers for Xf resistance from this resistance source, it will be relatively easy to incorporate this form of resistance with sources carrying PdR1 at later stages of the program, with the goal of broadening resistance.

V. arizonica b40-14 – Over the last 7 years we have greenhouse tested 45 F1 progeny of PD susceptible V. rupestris Wichita Refuge crossed with PD resistant V. arizonica b40-14 (R89 series).  Forty-two were highly resistant and three had intermediate reactions (data not shown). In 2006, we made the 06339 cross (V. vinifera F2-35 x b40-14) and established 198 seedlings for testing.  In 2007, we crossed the V. vinifera variety Airen onto two of the PD resistant R89 series genotypes and planted a total of 163 genotypes in Spring 2008.  We have initiated greenhouse screening of these two populations for initial mapping of a new PdR locus (Table 2). From our previous testing of the R89 series, we expect all the F1 progeny of b40-14 crossed to V. vinifera to be PD resistant.  To date we have completed greenhouse testing of 7 genotypes; they all lack PD phenotypic symptoms and have low ELISA values.  We are planning on using the progeny of the 06339 x V. vinifera crosses made in 2008 (Table 1e.) for further mapping efforts to better characterize this very strong, and morphologically and genetically different source of PD resistance.

Given that low levels of X. fastidiosa exist in resistant plants it will be important to also have PD resistant rootstocks to graft with resistant scions and prevent them from dying on susceptible rootstocks.  Greenhouse screening results and horticultural evaluation of 8 promising progeny from crosses involving the rootstock 101-14 Mgt x F8909-08 (V. rupestris x V. arizonca b43-17) are shown in Table 3.  Evaluation for their rooting and grafting ability is in progress; selections that pass the rooting tests will be tested for PD resistance in the greenhouse.  Greenhouse screening for phylloxera and nematode resistance will be done on PD resistant selections followed by field testing.

Any new PD resistant variety should also be resistant to powdery mildew (PM). We have been exploring powdery mildew resistance in a number of backgrounds including Olmo’s VR (vinifera x rotundifolia) hybrids, which form the basis of international efforts at characterizing Run1, the rotundifolia-based locus responsible for resistance to PM.  In 2008 before planting to the field, we tested the feasibility of using MAS to simultaneously screen for PdR1 and the PM resistance locus Run1 from Olmo’s e-series (partially fertile VR hybrids).  We tested 320 genotypes and planted 40 genotypes with resistant markers to both PD and PM in the field.  An additional 590 seedlings from 14 different crosses of PdR1 x Run1 parents were planted in a nursery to screen for PM  resistance and vigor before MAS testing.  Subsequent MAS testing this Fall yielded 51 seedlings with flanking markers for both PdR1 and Run1.  These are the first examples of using MAS to screen for two such different grape diseases in the same genotype.  These PD & PM resistant genotypes are ~88% vinifera.  In the spring we made two crosses of our 88% PdR1 resistant selections with two ~94% vinifera selections carrying Run1 that we had advanced last year from Olmo’s e-series.  A total of 220 seeds were produced and the progeny are ~91% vinifera and we hope to have about 25% with resistance to both PD and PM (Table 1b). MAS test results are pending.

Beringer Field Testing

Selections from the BC3, 94% vinifera crosses from the 07-355 (U0505-01 x Petite Sirah) and 07-370 (vinifera F2-35 x U0502-38) populations have been grafted onto Dog Ridge (currently the only certified virus-free PD resistant rootstock) on February 17, 2009 and will be planted at Beringer this Spring.  These genotypes have been marker tested and their PD resistance status will be confirmed by greenhouse testing in the coming months.  Inoculation in the field should take place in spring 2010. Selections from the 045554 (BC2, 88% vinifera) population were needle inoculated for the first time on May 22, 2008.  Selections from the A81 population (BC1, 75% vinifera) with the PdR1b (F8909-08) allele were inoculated for the second time.  Both were sampled for ELISA testing on October 16, 2008.  Table 4 shows that the agreement of markers, greenhouse screen ELISA results and field results are excellent, and demonstrate the robust PD resistance of PdR1.  We recently grafted nine of our most promising 88% vinifera PdR1 wine types (2 white and 7 red) onto Dog Ridge for planting at Beringer this Spring with enough vines for small scale winemaking trials.

Wine Making

Four of the eight advanced selections containing PdR1 that are 87.5% vinifera from crosses with Syrah and Chardonnay, which we propagated for small-scale wine making tests, set enough fruit to conduct small scale fermentations in Fall 2008.  Sensory evaluation of these wines is summarized in Table 5.  Note that sensory tasting scores for the PD resistant hybrids distribute themselves around the classic vinifera varieties.  Fruit evaluation and must analysis from numerous other genotypes from crosses involving elite wine cultivars were reported in our October 13, 2008 progress report.

V.  Publications or Reports from this Project

Fritschi, F.B., H. Lin and M.A. Walker.  2008.  Scanning electron microscopy reveals different plant-pathogen interaction pattern in four Vitis genotypes infected with Xylella fastidiosa.  Plant Dis 92:276-286.

Riaz, S., A.C. Tenscher, B.P. Smith, D.A. Ng and M.A. Walker.  2008.  Use of SSR markers to assess identity, pedigree, and diversity of cultivated muscadine grapes.  J Amer Soc Hortic Sci 133:559-568

Doddapaneni, H., H. Lin, M.A. Walker, J. Yao and E.L. Civerolo.  2008.  VitisExpDB:  a database resource for grape functional genomics.  BMC Plant Biol 8:23.

Riaz, S., A.C. Tenscher, J. Rubin, R. Graziani, S.S. Pao and M.A. Walker.  2008.  Fine-scale genetic mapping of two Pierce’s disease resistance loci and a major segregation distortion region on chromosome 14 of grape.  Theor Appl Genet 117:671-681

Vezzulli S., D. Micheletti, S. Riaz, M. Pindo, P. This, M.A. Walker, M. Troggio and R. Velasco.  2008. A wide SNP transferability survey within the genus Vitis. BMC Plant Biol 8:128

Lowe, K.M., S. Riaz and M.A. Walker.  2008.  Variation in recombination rates across Vitis species.  Tree Genome Genet 5:71-80

Stover, E., S. Riaz and M.A. Walker.  2008.  PCR screening for Xylella fastidiosa in grape genebank accessions collected in the south eastern United States.  Amer J Enol Viticult 59:437-439.

Riaz, S., A.C. Tenscher, R. Graziani, A.F. Krivanek and M.A. Walker.  2009.  Using marker-assisted selection to breed Pierce’s disease resistant grapes.  Amer J Enol Viticult 60(2):(In press)

VI. Presentations on PD Research

Progress breeding PD resistant wine, table and raisin grapes.  San Joaquin Valley Consolidated Pest Control District Meeting, Delano, CA  April 3, 2008.

Walker breeding program.  American Vineyard Foundation Board Meeting, Modesto, CA, April 25, 2008.

Using marker-assisted selection to breed for Pierce’s disease resistance in grape.  American Society for Viticulture and Enology Annual Meeting, Portland, OR, June 18, 2008.

The hunt for resistance genes to combat Pierce’s disease.  National Viticultural Research Conference, Davis, CA, July 11, 2008.

Genetic and phenotypic resistance to Pierce’s disease in Vitis arizonica/candicans selections from Monterrey, Mexico (J. Rubin). National Viticultural Research Conference, Davis, CA, July 11, 2008.

Pierce’s disease:  incidence, spread and control.  Australian Society for Viticulture and Oenology Disease Workshop, Mildura, Australia, July 24, 2008.

Breeding PD resistant table grapes.  Del Monte Grower’s Association, Davis, CA, September 26, 2008.

Grape breeding at UC Davis.  Integrated Winegrowing partners and growers.  Sebastopol, CA , November 20, 2008.

Creating Xylella fastidiosa resistant grapevines by conventional breeding.  CDFA PD/GWSS Research Meeting, San Diego, CA  December 17, 2008.

VII. Research Relevance Statement

This project continues to breed PD resistant winegrapes with the primary focus on the PdR1 resistance source so that progress can be expedited with MAS. Populations with Xf resistance from other sources are being maintained and expanded, but progress is slower with these sources. We continue to supply plant material, conduct greenhouse screens and develop new mapping populations for our companion project on fine-scale mapping of PD resistance leading to the characterization of the PdR1 resistance.  The second testing of small-scale wine from advanced selections with 87.5% vinifera from winegrapes was done in Fall 2008, and they scored remarkably well.

VIII. Lay Summary

Progress continues on breeding Pierce’s disease (PD) resistant winegrapes and has been greatly accelerated by the incorporation of marker-assisted selection (MAS) for the Pierce’s disease resistance gene, PdR1 (see companion report).  The use of MAS and our acceleration of the seed to seed breeding cycle to three years has allowed very rapid progress towards PD resistant winegrapes. Populations from the 2007 crosses were screened with MAS for both PD and powdery mildew (Run1) where appropriate and only those with the markers were planted in the field.  The 2008 crosses are currently being screened by MAS and will be planted in the field this Spring.  Results from needle inoculation with X. fastidiosa of both the 75% and 87.5% vinifera PdR1 scions planted in field trials at Beringer in Napa County found that these selections have very strong resistance to PD in the greenhouse and field. Finally, small scale wine lots were made from four 87.5% vinifera PdR1 containing wine grape selections for the second year, and they scored remarkably well.  Fruit evaluation and must analysis were performed on numerous other promising progeny of 87.5% vinifera PdR1 lines.

IX. Status of Funds

These funds are scheduled to be spent by the end of the grant.

X.  Summary and Status of Intellectual Property Produced

Thus far no selections have been released from this breeding program.  When they are they will be released through UC Davis.

Table 1. 2008 wine and rootstock type crosses, numbers of seeds & seedlings produced with number marker tested.

| Resistant Type | Vinifera Parent of Resistant Type | Vinifera Types used in 2007 crosses | Actual Seeds | # Seedlings Produced | # Marker Tested |
| --- | --- | --- | --- | --- | --- |
| 1a. Monterrey V. arizonica/candicans resistance source (F8909-08)to produce progeny with 93.75% V. vinifera parentage. |
| U0502 | Chardonnay | F2-7 | 262 | 114 | 50 |
| U0505 | Cabernet Sauvignon | Tannat | 694 | 151 | 100 |

Table 1. cont’d

| 1b. Monterrey V. arizonica/candicans resistance source (F8909-08) and Run1 PMR to produce progeny with 90.6% V. vinifera parentage. |
| --- |
| U0502 | Chardonnay | 06353, e78 allele pattern | 82 | pending | pending |
| U0505 | Cabernet Sauvignon | 06717, e78 allele pattern | 138 | pending | pending |
| 1c. Monterrey V. arizonica/candicans resistance source (F8909-08) and a vinifera PM resistance source to produce progeny with 87.5% V. vinifera parentage. |
| A81-17 | A38-7 | Karadzhandal | 330 | 301 | 150 |
| 1d. Monterrey V. arizonica/candicans resistance source (F8909-17 allele) to produce progeny with 87.5% V. vinifera parentage. |
| 06324 | Chenin blanc | Airen, Cabernet Sauvignon, Chardonnay, Malaga Rosada, Tannat | 612 | 402 | 250 |
| 06372 | Malaga Rosada | Clairette blanche, Tannat | 947 | 716 | 455 |
| 06381 | F2-7 (Cab x Carignane) | Tannat | 151 | 113 | 75 |
| 1e. Other PD resistance sources: b40-14 V. arizonica (06339) progeny are 87.5% V. vinifera. The V. shuttleworthii PD resistance sources 0098-03 progeny are 87.5% V. vinifera and 04394 progeny are 75% V. vinifera |
| 06339 | F2-35 (CS x Carig) | Tannat | 325 | pending | NR |
| 9985-03 | Ruby Seedless | Cabernet Sauvignon, Chardonnay | 324 | pending | NR |
| 04394 | Flame Seedless | Cabernet Sauvignon, Clairette blanche, F2-35, Tannat | 773 | pending | NR |
| 1f. Rootstock crosses to combine PD and nematode resistance. |
| 03300-048 | 06301,Wyoming Riparia, Riparia Gloire, 44-53 mgt |  | 1397 | pending | MAS Test after hort evaluation |

| Table 2. PD resistant winegrape progeny just completed or currently in greenhouse screening for PD resistance. |
| --- |
| Group | Genotypes | # Genotypes | Inoculation Date | ELISA Date | Resistance Source(s) |
| A | PdR1 recombinants; propagation type & pot size; | 46 | 10/9/2008 | 1/15/2009 | F8909-08 |
| B | 2008 PdR1 Parents, mini-mapping, e6-23 VR series | 47 | 11/25/2008 | 2/26/2009 | b43-17 (both alleles), VR |
| C | 07744 mapping population | 85 | 12/16/2009 | 3/26/2009 | b40-14 |
| D | Greenhouse spacing trial |  | 1/15/2009 | 4/16/2009 | F8909-08 |
| E | 07386 Mapping population | 45 | 2/3/2009 | 5/5/2009 | b40-14 |

Table 3. Promising PD resistant rootstocks with greenhouse PD screen and horticultural trait scores.

| Genotype | Parents | MAS PdR1 | Sex | Vigor | 2007 Rooting % @ 21 day | 2008 GH PD Screen Results | 2007-8 Consensus Rootstock phenotype 1=v. good, 5=discard |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 03300-047 | 101-14 x F8909-08 | U | M | h-v high | 50% | 7,585 | 1.8 |
| 03300-082 | 101-14 x F8909-08 | R | M? | high | 100% | 29,001 | 1.9 |
| 03305-18 | 101-14 x F8909-08 | R | F | high | 100% | 30,220 | 2.5 |
| 03305-12 | 101-14 x F8909-08 | R? | F | h-v high | 100% | 32,632 | 2.0 |
| 03300-048 | 101-14 x F8909-08 | R | F | high | 100% | 44,234 | 1.5 |
| 06304-26 | 03300-088 x 9621-152 | R | F | mod-high | 90% | 60,062 | 2.0 |
| 03300-072 | 101-14 x F8909-08 | U | M | high | 30% | 94,820 | 2.0 |
| 03300-099 | 101-14 x F8909-08 | R | F | mod-high | 100% | 102,813 | 1.0 |
| 101-14 | riparia x rupestris | none | F | mod-high | 100% | 858,055 | 1.0 |
| UCD GRN-4 | synonym: 9365-85 | none | M | mod | 100% | 3,956,812 | 1.0 |

Table 4. Summary of greenhouse (GH) and several years field ELISA means for genotypes with (R) and without (S) the PdR1 marker.

| Group | % Vinifera | N (geno-types) | PdR1 Marker Score or GH score | 2008 mean ELISA cfu/ml (field) | 2007 mean ELISA cfu/ml (field) | 2006 mean ELISA cfu/ml (field) | mean ELISA cfu/ml (Green-house) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 04-5554 | 88% | 12 | R | 52,374 | - | - | 157,037 |
| 04-5554 | 88% | 6 | S | 4,634,182 | - | - | 6,356,825 |
| A81 | 75% | 15 | R | 46,685 | 93,362 | 114,044 | 94,875 |
| A81 | 75% | 5 | S | 2,550,697 | 2,680,311 | 1,193,770 | 2,895,812 |
| Roucaneuf | 56% | 1 | R | 415,864 | 235,573 | - | 681,000 |
| Blanc du Bois | 66% | 1 | R | 467,756 | - | - | 681,000 |
| Chardonnay | 100% | 1 | S | 3,807,851 | 1,561,321 | 956,124 | 6,500,000 |

Table 5. Results of a blind tasting of 2008 vintage wines tasted 12/9/08 by 10 tasters comprised of faculty and staff in the department of Viticulture & Enology, UCD.  The wines were rated on a hedonic quality scale from 1 = poor to 5 = v. good.

| Wine name | Group Total | Low score | High Score | Consensus Descriptors: color; aroma; flavor-texture |
| --- | --- | --- | --- | --- |
| U0502-20 | 34.0 | 2 | 5 | pale yellow-green; pineapple, grassy, gooseberry, lemon zest; smooth with a nice acid balance |
| Syrah | 32.8 | 2 | 4 | dark red-purple; plum, mint, fruity, violets; rich, chewy tannins, good length. |
| Chardonnay | 32.3 | 2 | 5 | light yellow; tropical, aromatic, pear, melon; round, warm finish |
| U0501-12 | 30.5 | 1 | 4 | dark red-purple; stone fruit, raspberry; medium body, more acidic and elegant |
| U0502-10 | 30.5 | 1 | 4 | medium red; stone fruit, raspberry, smokey, red licorice; simple but pleasing structure |
| Lenoir | 26.0 | 1 | 4 | dark red w\ brown; porty, stewed fruit, raisined; oxidized, flabby |
| Pinot noir | 21.0 | 1 | 3.5 | brick; cherry, berry, earthy, gamey; lacks structure, hot |
| U0502-01 | 20.3 | 1 | 3 | light red; candy, sweet cherry; thin |